## Team Members
Team Member | Contact Phone | Normal Hours | Normal Workdays
Colin Staub | 719-502-6877 | 8 | Mon - Fri
Grace Murray | 781-484-6444 | 8 | Mon - Fri
Emma Marshall | 970-946-6095 | 8 | Mon - Fri
Robert Jimenez | 720-253-6576 | 8 | Mon - Fri

## Roles
Role | Team Member
Project Manager | Bob Smith
Documentation Developer | Bob Smith
Data Warehouse Developer | Sue Jones
ETL developer | Sue Jones
Cube Developer | Sue Jones
Report Developer | Sue Jones
Testers | Tim Thomas
Release Manager | Tim Thomas

## Solution Schedule
BI Solution Projects | Est Hours | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri
Interview and Identify: | 28 | Mon: ***************************************
Planning and Documenting: | 18 | Thur: **************************
Create the Data Warehouse | 3 | Mon: ****
Extract, Transform, and Load: | 6 | Mon: **********
Create Cubes: | 6 | Mon: ********
Create Reports: | 6 | Mon: ********
Test the Solution: | 21 | Mon: **; Tue: *************************
Approve, Release, and Prepare for next version: | 9 | Thur: *****************

## Estimated Hours
BI Solution Projects | Task | Action Item | Estimated Hours | Actual Hours
Interview and Identify: | Interviews | Talk To Business Owner | 3
|  | Talk to Mangers | 3
|  | Talk to Users | 3
|  | Talk to DBA | 3
| Document Requirements | Create an informal overview | 3
|  | Create a BI solution worksheet | 3
| Locate Data | Review database tables | 3
|  | Review invoice documents | 3
|  | Review sales awards program | 3
| Discuss Feasibility | Decide if the solution will work | 1
28
Planning and Documenting: | Define Team Roles | What role fit this solution? | 1
| Define Team Members | Who will fill each role? | 1
| Define Team Schedule | When will we need them? | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Define IT requirements | Decide which Server will we use for DW, SSIS, SSAS, SSRS | 1
|  | Verify a time slot of Solution automation jobs | 1
| Define Security requirements | Decide which groups will have access to what? | 1
| Define Licensing requirements | Verify that the company has sufficient licensing | 3
| Estimate the cost | Hours * Wages + and additional 10% for unknowns | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Create formal documents | Complete BI solution worksheet | 3
|  | Create a Development Document | 3
18
Create the Data Warehouse | Create the Database | Create the Tables | 2
|  | Define Constraints | 1
3
Extract, Transform, and Load: | Create ETL Code | Create a SQL Script with ETL code | 3
|  | Create a an SSIS package with ETL code | 3
6
Create Cubes: | Create SSAS Database | Create Dimensions | 3
|  | Create Cubes | 3
6
Create Reports: | Create Prototype Reports | Create SSRS Reports | 3
|  | Create Excel Reports | 3
6
Test the Solution: | Requirements | Verify naming | 3
|  | Verify data domains | 3
|  | Verify formula results | 3
|  | Verify presentation formatting | 3
| Performance | Test SSIS ETL performance | 3
|  | Test SSAS Processing performance | 3
|  | Test SSRS Report performance | 3
21
Approve, Release, and Prepare for next version: | Finalize formal documents | Finish development document | 3
|  | Create a formal overview document | 3
|  | Create a lessons learned document | 3
9
|  | TOTAL | 106.7

## Data Warehouse
Data Warehouse Objects Worksheet
Object Name | Description | Source | Source Type | Destination Type
DWRedwood | Data Warehouse | Redwood OLTP | Database | Database
DWRedwoodListing.dbo.FactListing | Fact Table | Redwood.dbo.Listing | Table | Table
DWRedwood.dbo.ListingID | Dimension Key Column | Redwood.dbo.Listing.ListingID | int | int
DWRedwood.dbo.FactListing.SaleStatusID | Dimension Key Column | Redwood.dbo.Listing.SaleStatusID | int | int
DWRedwood.dbo.BeginListDate | Dimension Column | Redwood.dbo.Listing.BeginListDate | datetime | datetime
DWRedwood.dbo.EndListDate | Dimension Column | Redwood.dbo.Listing.EndListDate | datetime | datetime
DWRedwood.dbo.FactListing.PropertyID | Dimension Key Column | Redwood.dbo.Listing.PropertyID | int | int
DWRedwood.dbo.AskingPrice | Measure Column | Redwood.dbo.Listing.AskingPrice | money | money
DWRedwood.dbo.Factisting.ListingAgentID | Dimension Key Column | Redwood.dbo.Listing.ListingAgentID | int | int
DWRedwood.dbo.DimProperty | Dimesion Table | Redwood.dbo.Property | Table | Table
DWRedwood.dbo.DimProperty.PropertyID | Dimension Key Column | Redwood.dbo.Property.PropertyID | int | int
DWRedwood.dbo.DimProperty.City | Dimension Column | Redwood.dbo.Property.City | nvarchar(30) | nvarchar(30)
DWRedwood.dbo.DimProperty.State | Dimension Column | Redwood.dbo.Property.State | nvarchar(20) | nvarchar(20)
DWRedwood.dbo.DimProperty.ZipCode | Dimenson Column | Redwood.dbo.Property.Zipcode | nvarchar(20) | nvarchar(20)
DWRedwood.dbo.DimProperty.Bedrooms | Dimenson Column | Redwood.dbo.Property.Bedrooms | int | int
DWRedwood.dbo.DimProperty.Bathrooms | Dimenson Column | Redwood.dbo.Property.Bathrooms | int | int
DWRedwood.dbo.DimProperty.Stories | Dimenson Column | Redwood.dbo.Property.Stories | int | int
DWRedwood.dbo.DimProperty.SQFT | Dimenson Column | Redwood.dbo.Property.SQFT | int | int
DWRedwood.dbo.DimProperty.YearBuilt | Dimension Column | Redwood.dbo.Property.YearBuilt | numeric(4,0) | numeric(4,0)
DWRedwood.dbo.DimAgent | Dimesion Table | Redwood.dbo.Agent | Table | Table
DWRedwood.dbo.DimAgent.AgentID | Dimension Key Column | DWRedwood.dbo.Agent.AgentID | int | int
DWRedwood.dbo.DimAgent.FirstName | Dimension Column | DWRedwood.dbo.Agent.FirstName | nvarchar(30) | nvarchar(30)
DWRedwood.dbo.DimAgent.LastName | Dimension Column | DWRedwood.dbo.Agent.LastName | nvarchar(30) | nvarchar(30)
DWRedwood.dbo.DimAgent.Gender | Dimension Column | DWRedwood.dbo.Agent.Gender | nchar(1) | nchar(1)
DWRedwood.dbo.DimAgent.BirthDate | Dimension Column | DWRedwood.dbo.Agent.BirthDate | datetime | datetime
DWRedwood.dbo.DimAgent.HireDate | Dimension Column | DWRedwood.dbo.Agent.HireDate | datetime | datetime
DWRedwood.dbo.DimSaleStatus | Dimesion Table | Redwood.dbo.SaleStatus | Table | Table
DWRedwood.dbo.DimSaleStatus.SaleStatusID | Dimension Key Column | Redwood.dbo.SaleStatus.SaleStatusID | int | int
DWRedwood.dbo.DimSaleStatus.SaleStatus | Dimension Column | Redwood.dbo.SaleStatus.SaleStatus | nvarchar(10) | nvarchar(10)
DWRedwood.dbo.DimDates | Dimesion Table | na | na | Table
DWRedwood.dbo.DimDates.DateKey | Dimension Column | DWRedwood.dbo.DimDates.DateKey | na | int
DWRedwood.dbo.DimDates.Date | Dimension Column | DWRedwood.dbo.DimDates.Date | na | datetime
DWRedwood.dbo.DimDates.DateName | Dimension Column | DWRedwood.dbo.DimDates.DateName | na | nvarchar(50)
DWRedwood.dbo.DimDates.Month | Dimension Column | DWRedwood.dbo.DimDates.Month | na | int
DWRedwood.dbo.DimDates.MonthName | Dimension Column | DWRedwood.dbo.DimDates.MonthName | na | nvarchar(50)
DWRedwood.dbo.DimDates.Quarter | Dimension Column | DWRedwood.dbo.DimDates.Quarter | na | int
DWRedwood.dbo.DimDates.QuarterName | Dimension Column | DWRedwood.dbo.DimDates.QuarterName | na | nvarchar(50)
DWRedwood.dbo.DimDates.Year | Dimension Column | DWRedwood.dbo.DimDates.Year | na | int
DWRedwood.dbo.DimDates.YearName | Dimension Column | DWRedwood.dbo.DimDates.YearName | na | nvarchar(50)
Object Name | Description | Source | Source Type | Destination Type

## ETL Objects
SSIS ETL Objects Worksheet
Object Name | Type | Description | Source | Destination

## Cubes and Dimensions
SSAS Objects Worksheet
Object Name | Description